## Sheet1
Actor | Module | Task | Price | Cost to Add in System Admin role | Completion Phase
Sys Admin | Lender Creation | List to display all lender | 1500 |  | Phase 1
Sys Admin |  | Edit Each lender | 1500 |  | Phase 1
Sys Admin |  | Delete each lender | 1500 |  | Phase 1
Sys Admin |  | Add new lender | 1500 |  | Phase 1
Sys Admin | Credit checker Creation | List to display all Credit checker | 1500 |  | Phase 1
Sys Admin |  | Edit Each Credit checker | 1500 |  | Phase 1
Sys Admin |  | Delete each Credit checker | 1500 |  | Phase 1
Sys Admin |  | Add new Credit checker | 1500 |  | Phase 1
Sys Admin | Sales Eecutive Creation | List to display all Sales Eecutive | 1500 |  | Phase 1
Sys Admin |  | Edit Each Sales Eecutive | 1500 |  | Phase 1
Sys Admin |  | Delete each Sales Eecutive | 1500 |  | Phase 1
Sys Admin |  | Add new Sales Eecutive | 1500 |  | Phase 1
Borrower | Borrower Additional Info/Action Required. | Action Required List/Additional info lists. | 1500 | 500
Borrower | Borrower Additional Info/Action Required. | Additional info Response page + Addition document upload specific to lender. | 3000 | 1000
Borrower | Borrower Loan Request | Loan request List | 1500 | 1000 | Phase 2
Borrower | Borrower Loan Request | Create loan Request form | 2500 | 1000 | Phase 2
Borrower | Borrower Loan Request | Edit Loan requet form | 2500 | 1000 | Phase 2
Borrower | Borrower Loan Request | View Loan Request (Loan details + Additional info + document download link) | 3000 | 1000
Sys Admin | System Admin Sales Executive Mapping | List of Loan Request to Sales executive mapping. With feature to list unmapped loan request. | 2500
Sys Admin | System Admin Sales Executive Mapping | Map Sales executive to Loan request. | 1500
Sys Admin | System Admin Credit checker Mapping | List of Loan Request to Credit checker mapping. With feature to list unmapped loan request. | 2500
Sys Admin | System Admin Credit checker Mapping | Map Credit checker to Loan request. | 1500
Sales Exe. | Sales executive background check | List of Loan reuest mapped to sales executive that are pendign for background check. | 2500 | 1000
Sales Exe. | Sales executive background check | Approve/Reject Loan request | 1500 | 1000
Sales Exe. | Sales executive background check | Generete Mandate letter and mail to borrower. | 3000 | 1000
Borrower | Borrower Document | Document Upload | 1500 | 1000
Borrower | Borrower Document | View Document | 1500 | 500
Borrower | Borrower Document | Delete document | 1500 | 1000
Credit checker | Credit checker Approve Reject | List of Loan reuest mapped to Credit checker that are pendign for Credit check. | 2500 | 1000
Credit checker | Credit checker Approve Reject | Reject Credit check | 1500 | 1000
Credit checker | Credit checker Approve Reject | Generate executive summary report. | 2500 | 1000
Credit checker | Credit checker Approve Reject | Edit Executive summary report. | 2500 | 1000
Credit checker | Credit checker Approve Reject | Credit checker Request additional info | 1500 | 1000
Lender | Lender Action | List of Loan requet where loan request amont Lender Minimum ticket size < borrower requested amount < Lender Maximum ticket size. And pending for Lender action | 3000 | 1000
Lender | Lender Action | Lender approves/Rejects | 1500 | 1000
Lender | Lender Action | Lender ask for additional info | 1500 | 1000
Lender | Lender Action | Lender view Loan request -- Covered in borrowe view. | 0
| Role wise Access |  | 5000
| Change Password, Forgot password, Login |  | 3000
76000
44000

## Sheet2
Brief summary of Work | Cost in Rs | Development phase
Lender creation Create, edit, Delete, View, List of Lenders with paging, sorting and perch by name. | 8000 | Phase 1
Credit checker creation Create, edit, Delete, View, List of Credit checkers with paging, sorting and search by name. | 8000 | Phase 1
Sales executive creation | 8000 | Phase 1
Role wise access to each page | 10000 | Phase 4
Login page, change password, Forgot password | 8000 | Phase 4
Borrower Loan request, Loan request form, Send to appropriate sales executive, delete loan request, Edit loan request, document upload and edit | 20000 | Phase 2
Borrower additional information response request pages | 15000
Sales executive background check, mandate letter, forward to credit checker | 15000 | Phase 2
Credit checker loan approval, rejection, additional request, forward to lender, Executive summary report generation and edit. | 20000 | Phase 3
Lender Loan request approval additional info request, view loan request, reject loan request. | 15000 | Phase 3
Replicate all the functionality to system admin | 25000 | Phase 5
Delivery date of phases | Delivery data
Phase 1 | 2017-09-23
Phase 2 | 2017-10-02
Phase 3 and Phase 4 | 2017-10-15