## Sheet1
Actor | Module | Task | Price | Cost to Add in System Admin role | Completion Phase
Sys Admin | Lender Creation | List to display all lender | 1500 |  | Phase 1
Sys Admin |  | Edit Each lender | 1500 |  | Phase 1
Sys Admin |  | Delete each lender | 1500 |  | Phase 1
Sys Admin |  | Add new lender | 1500 |  | Phase 1
Sys Admin | Credit checker Creation | List to display all Credit checker | 1500 |  | Phase 1
Sys Admin |  | Edit Each Credit checker | 1500 |  | Phase 1
Sys Admin |  | Delete each Credit checker | 1500 |  | Phase 1
Sys Admin |  | Add new Credit checker | 1500 |  | Phase 1
Sys Admin | Sales Eecutive Creation | List to display all Sales Eecutive | 1500 |  | Phase 1
Sys Admin |  | Edit Each Sales Eecutive | 1500 |  | Phase 1
Sys Admin |  | Delete each Sales Eecutive | 1500 |  | Phase 1
Sys Admin |  | Add new Sales Eecutive | 1500 |  | Phase 1
Borrower | Borrower Additional Info/Action Required. | Action Required List/Additional info lists. | 1500 | 500
Borrower | Borrower Additional Info/Action Required. | Additional info Response page + Addition document upload specific to lender. | 3000 | 1000
Borrower | Borrower Loan Request | Loan request List | 1500 | 1000 | Phase 2
Borrower | Borrower Loan Request | Create loan Request form | 2500 | 1000 | Phase 2
Borrower | Borrower Loan Request | Edit Loan requet form | 2500 | 1000 | Phase 2
Borrower | Borrower Loan Request | View Loan Request (Loan details + Additional info + document download link) | 3000 | 1000
Sys Admin | System Admin Sales Executive Mapping | List of Loan Request to Sales executive mapping. With feature to list unmapped loan request. | 2500
Sys Admin | System Admin Sales Executive Mapping | Map Sales executive to Loan request. | 1500
Sys Admin | System Admin Credit checker Mapping | List of Loan Request to Credit checker mapping. With feature to list unmapped loan request. | 2500
Sys Admin | System Admin Credit checker Mapping | Map Credit checker to Loan request. | 1500
Sales Exe. | Sales executive background check | List of Loan reuest mapped to sales executive that are pendign for background check. | 2500 | 1000
Sales Exe. | Sales executive background check | Approve/Reject Loan request | 1500 | 1000
Sales Exe. | Sales executive background check | Generete Mandate letter and mail to borrower. | 3000 | 1000
Borrower | Borrower Document | Document Upload | 1500 | 1000
Borrower | Borrower Document | View Document | 1500 | 500
Borrower | Borrower Document | Delete document | 1500 | 1000
Credit checker | Credit checker Approve Reject | List of Loan reuest mapped to Credit checker that are pendign for Credit check. | 2500 | 1000
Credit checker | Credit checker Approve Reject | Reject Credit check | 1500 | 1000
Credit checker | Credit checker Approve Reject | Generate executive summary report. | 2500 | 1000
Credit checker | Credit checker Approve Reject | Edit Executive summary report. | 2500 | 1000
Credit checker | Credit checker Approve Reject | Credit checker Request additional info | 1500 | 1000
Lender | Lender Action | List of Loan requet where loan request amont Lender Minimum ticket size < borrower requested amount < Lender Maximum ticket size. And pending for Lender action | 3000 | 1000
Lender | Lender Action | Lender approves/Rejects | 1500 | 1000
Lender | Lender Action | Lender ask for additional info | 1500 | 1000
Lender | Lender Action | Lender view Loan request -- Covered in borrowe view. | 0
| Role wise Access |  | 5000
| Change Password, Forgot password, Login |  | 3000
76000
44000

## Sheet2
Brief summary of Work | Cost in Rs | Development phase
Lender creation Create, edit, Delete, View, List of Lenders with paging, sorting and perch by name. | 8000 | Phase 1
Credit checker creation Create, edit, Delete, View, List of Credit checkers with paging, sorting and search by name. | 8000 | Phase 1
Sales executive creation | 8000 | Phase 1
Role wise access to each page | 10000 | Phase 4
Login page, change password, Forgot password | 8000 | Phase 4
Borrower Loan request, Loan request form, Send to appropriate sales executive, delete loan request, Edit loan request, document upload and edit | 20000 | Phase 2
Borrower additional information response request pages | 15000
Sales executive background check, mandate letter, forward to credit checker | 15000 | Phase 2
Credit checker loan approval, rejection, additional request, forward to lender, Executive summary report generation and edit. | 20000 | Phase 3
Lender Loan request approval additional info request, view loan request, reject loan request. | 15000 | Phase 3
Replicate all the functionality to system admin | 25000 | Phase 5
Delivery date of phases | Delivery data | Amount
Phase 1 | 2017-09-23 | 24000
Phase 2 | 2017-10-02 | 35000 | 59000
Phase 3 and Phase 4 | 2017-10-15

## Sheet3
Stages |  | Document Checklist | Folder Structure
Active Pre Lead | Borrower makes request. | KYC Documents | Confidential
Pre Lead Client Drop | Borrower or Systme Admin deletes loan request. | Certificate of Incorporation | Public
Active Stage 1 Lead | Background verification done Mandate letter generated | MOA and AOA | Subfolders under Public
Stage 1 Reject | Sales rep. Rejects loan request at time of background verification. | Pan Card of Company | KYC
Stage 1 Client Drop | Borrower or Systme Admin deletes loan request. | List of Directors | Financials
Active Stage 2 Lead | Borrower upload document after successful background check | Pan Cards of all directors | Tax Returns
Stage 2 Reject | Credit checker reject loan req. | Address Proof of all directors | Bank Statements
Stage 2 Client Drop | Borrower or Systme Admin deletes loan request. | Financial Statements | PO and Invoice
Active Listing | Credit checker approves loan request and loan request is forwareded to Lenders | Audited financials for past three years | Other
Post Listing Client Drop | Borrower or Systme Admin deletes loan request. | Audit Report and Tax Audit Report for last 3 years | Lender 1 Additional Info
Lender Reject | Lender rejects | Provisional financials for current year | Lender 2 Additional Info
Active Sanction | Lender senction loan request | Projected financials for loan term | Lender 3 Additional Info
Sanctioned Client Drop | Borrower or Systme Admin deletes loan request. | Past Investments
Sanctioned Lender Drop | ?? | Shareholding Pattern
Disbursed | ?? | Year-wise breakup of equity investment received (amount and investor)
Active Repeat Listing | ?? | Loans and Banking
List of all bank accounts maintained by the company
Bank Statements for ALL bank accounts for the last 12 months
Term sheets for all loans and credit facilities currently outstanding
Business
Company profile and brochure, if any
Latest investor presentation deck
Organisation Structure
Statutory Returns
Income Tax Returns for the last 2 years
VAT and/or service tax returns for the last 12 months
For Unsecured Business Loans or Invoice Discounting
List of Top Customers (Top 10 customers or top 50% sales)
Debtor Ageing Schedule
Customer contracts
Customer ledgers for top 10 customers
For PO based loan
Copy of the contract
Tender on which basis the contract was awarded
Milestones and expected payments/receipts for the project
Case studies - similar projects executed in the past
For term loan and leasing
Breakup of project cost
List of assets to be purchased
Technical specifications of proposed project
List of suppliers
Cash flow projections for the project